## HIGH-LEVEL PROCESS TABLE
INTERIM SDU CREATION HIGH-LEVEL PROCESS
PROCESS PURPOSE |  | To establish the process for the creation of an Interim Service Delivery Unit (SDU) starting from the assessment of need until until the completion of all activities and requirements needed to activite the start of its interim operations.
PROCESS SCOPE |  | This process applies to SEOReseller's Operations Department.
REFERENCES |  | DEFINITION OF TERMS LINK | PROCESS FLOWCHART LINK | POLICY | TEMPLATES & ANNEXES
NO | TRIGGER / INPUT | PROCESS | SUB-PROCESSES / ACTIVITIES | RASCI | RESOURCES / TOOLS | TIMELINE | OUTPUT(S) | QUALITY CHECKPOINT
A | SDU Revenue Performance | SDU Eligibility Assessment | 1. Check SDU Revenue Performance 2. Check SDU Production Hours Spent 3. Check SDU Manpower Count 4. Check Forecast for New Sales 5. Endorse SDU Creation | R - BI Manager A - BI Manager S - SDU Manager C - Workforce I - Operations Manager | Compass Sales Report Sales Forecast Email | >3 MONTHS | SDU Expansion Endorsement Report | Endorsement Report Review by Operations Manager
B | SDU Expansion Endorsment Report | Account Manager Nomination | 1. Check AM Revenue Performance 2. Check AM Certification Program Completion 3. Nomination of AM Candidate | R - SDU Manager A - SDU Manager S - L&D Manager C - BI Manager I - Operations Manager | Interim SDU Certification Profile Sales Report Email | 1 HOUR | AM Nomination Email | Review of Nomination Credentials by Operations Manager
C | Request for AM Certification Review | AM Interim SDU Certification Review | 1. Check AM Certification Record 2. Confirm AM's Interim SDU Certification Completion 3. Endorse AM as Interim SDU Manager | R - L&D Manager A - SDU Manager I - Operations Manager | Interim SDU Certification Profile Email | 1 HOUR | AM Qualification Confirmation | Review of AM Certifcation Completion by L&D
D | Candidate Interim SDU Manager | Interim SDU Proposal | 1. Determine Profile of Accounts to be Transferred 2. Develop Manpower Plan 3. Develop Asset Plan 4. Develop SDU Expense & Timeline Proposal 5. Present the Interim SDU Proposal 6. Review & Approve Interim SDU Proposal 7. Issue Interim SDU Proposal Approval Memo | R - Operations Manager A - Operations Manager S - SDU Manager / AM C - BI Manager I - Sr. Digital Ops. Mgr. | Manpower Plan Template Asset Plan Template Interim SDU Proposal Template Interim SDU Approval Memo Template | 3-4 WD | Interim SDU Approval Proposal Interim SDU Approval Memo | Review of the Interim SDU Proposal by the Sr. Digital Operations Manager
E | Interim SDU Approval Memo | Interim SDU Transition | 1. Inform Partners of the Transition 2. Communicate Interim SDU Approval to SDU Team 3. Hiring of Additional Headcount 4. Training & Certification of New Hires 5. Procurement of Admin & IT Assets 6. Transfer of Employee Credentials | R - SDU Manager; HR; Admin; IT A - Operations Manager S - SDU Manager C - SDU Manager I - Sr. Digital Operations Manager | Manpower Plan Asset Plan | > 3 MONTHS | Procured Assets Completed Training & Certifications | Check the progress of transition activities by the chosen Account Manager
F | Interim SDU Approval Memo | Interim SDU Mentoring | 1. Enroll AM in Interim SDU Mentoring Program 2. Assess AM and Develop Mentoring Plan 3. AM Undergp Mentoring by the SDU Manager 4. AM Complete Program Tasks & Activities 5. Check Completion of the Program | R - AM A - SDU Manager S - L&D C - L&D I - Operations Manager | Mentoring Plan Template AM Training & Certification Record | 2 MONTHS | Interim SDU Mentoring Completion Certificate | Review of the Program Completion by L&D
G. | Complete Interim SDU Team | Interim SDU Onboarding | 1. Formal Handover of Partners to New AM 2. Interim SDU Target Setting 3. Parent SDU and Interim SDU Alignment 4. Communicate Start of Interim SDU 5. Check Completeness of Onboarding Activities | R - Account Manager A - Operations Manager S - SDU Manager / AM C - BI Manager I - Sr. Digital Ops. Mgr. | Interim SDU Targets Interim SDU Policy? Onboarding Activities Checklist | 1-2 WD | Interim SDU Goals/Targets Organization Comms. | Check Completeness of Onboarding Activities

## Gantt Chart Presentation
1. AM Upskilling Program | 90 - 92 WD (3 Mos) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2. SDU Eligibility Assessment Process | 90 - 91 WD (3 Mos) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3. AM Nomination Process | 1 WD | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4. Interim SDU Proposal Preparation & Approval | 3 - 4 WD | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5. Interim SDU Manager Mentoring | 63 WD (2 Mos) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6. SDU Transition Process | 90 - 92 WD (3 Mos) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7. Interim SDU Onboarding Process | 1-2 WD | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
8. Start of Interim SDU Operations
|  | 90 WORKING DAYS ; 3 MONTHS | [89 empty] | 95 WORKING DAYS ; 3 MONTHS | [98 empty] | UNDEFINED
START OF ACTUAL SDU CREATION ACTIVITIES
START OF INTERIM SDU OPERATIONS

## Timelines Per Activity
SUB-PROCESS / ACTIVITY |  |  | CLASSIFICATION | DEPENDENCY | HRS | DURATION | TIMELINE | RESPONSIBLE | RESOURCES
1 | AM Upskilling Program
| A. | AM reaches 30K revenue w/ more than 1 year tenure | Required | START | - | 0 | 90 - 92 WD 3 Months | Acct, Manager
| B. | AM Enrollment Process | Required | 1.A | 1 HR | 1 |  | SDU Manager
| C. | Upskilling Course Accomplishment | Required | 1.B | - | 90 |  | SDU Manager , Acct. Manager
| D. | Upskilling Task Assignment Completion | Required | 1.C | -
| E. | Completion / Certification | Required | 1.D | 1 HR | 1 |  | L&D Manager
| F. | Retaking of Courses | Optional | 1.C | - | 1 |  | Accr. Manager
2 | SDU Eligibility Assessment Process
| A. | SDU reaches 100K revenue | Required | START | - | 0 | 90 - 91 WD 3 Months | BI Manager
| B. | SDU Revenue Performance Monitoring | Required | 2.A | - | 90 |  | BI Manager
| C. | Production Hrs & Headcount Checking | Required | 2.B | 1 HR | 1 |  | BI Manager
| D. | Email SDU Eligibility Recommendation Sending | Required | 2.B | 1 HR |  |  | BI Manager
| E. | Finalization of Monthly Report* | Optional | 2.B | - | x |  | BI Manager
3 | AM Nomination Process
| A. | AM Selection & Nomination | Required | 1. D, 2.D | 1 HR | 1 | 1 WD | SDU Manager
| B. | AM Qualification / Certification Review | Required | 2.A | 1 HR |  |  | L&D Manager
| C. | Email Interim SDU Selection | Required | 2.B | 1 HR |  |  | L&D Manager
| D. | AM Qualification / Certification Review of other Candidates | Optional | 2.B | 1 HR |  |  | L&D Manager
4 | Interim SDU Proposal Preparation & Approval
| A. | Profiling of Accounts to be Transferred | Required | 3 | 1 HR | 1 | 3 - 4 WD | Ops. Manager
| B. | Preparation of Manpower Plan | Required | 4.A | 1 HR |  |  | Ops. Manager
| C. | Preparation of Asset Plan | Required | 4.B. | 1 HR |  |  | Ops. Manager
| D. | Projection of Expense | Required | 4.C | 1 HR |  |  | Ops. Manager
| E. | Presentation of Proposal | Required | 4.D | - | 1 |  | Ops. Manager
| F. | Approval of Interim SDU Proposal | Required | 4.E | - |  |  | SDO Manager
| G. | Issuance of Interim SDU Approval Memo | Required | 4.F | 1 HR | 1 |  | SDO Manager
| H. | Revision of the Interim SDU Proposal* | Optional | 4.E | - | 1 |  | Ops. Manager
5 | Interim SDU Manager Mentoring
| A. | AM Enrollment in the Mentoring Program | Required | 4.G | 1 HR | 3 | 63 WD 2 Months | SDU Manager
| B. | AM Skills Assessment & Preparation of Mentoring Plan | Required | 5.A | - |  |  | L&D
| C. | Conduct Mentoring Activities | Required | 5.B | - | 30 |  | SDU Manager
| D. | Accomplish Mentoring Tasks / Projects | Required | 5.C. | - | 30 |  | Acct. Manager
| E. | Assessment of Mentoring Completion | Required | 5.D. | 1 HR |  |  | L&D
| F. | Issuance of Interim SDU Mentoring Clearance | Required | 5.E | 1 HR |  |  | L&D
6 | SDU Transition Process
| A. | Discussion of the Approval of the Interim SDU Approval | Required | 4.G | 1 HR | 1 | 90 - 92 WD 3 Months | Ops. Manager
| B. | Inform Employees who will be Transferred | Required | 6.A | 1 HR |  |  | Ops. Manager
| C. | Hiring of Additional Employees | Required | 6.B | - | 60 |  | HR
| D. | Procurement of Assets | Required | 6.B | - | 30 |  | Admin & IT
| E. | Training of Existing Employee for Mentoring/Promotion | Required | 6.B | - | 30 |  | Ops & L&D
| F. | Training & Certification of Newly-hired Employees | Required | 6.C | - | 30 |  | Ops & L&D
| G. | Transfer of Employee HR Credentials | Required | 6.C, 6.E | 1 HR | 1 |  | HR
| H | Transfer of Employee Operations Credentials | Required | 6.C, 6.E | 1 HR |  |  | Workforce
7 | Interim SDU Onboarding Process
| A. | Interim SDU Target Setting | Required | 6.H | 1 HR | 1 | 1 WD | Ops Manager
| B. | Parent SDU and Interim SDU Alignment | Required | 7.A | 1 HR |  |  | Ops Manager
| C. | Communication of the Start of Interim SDU Operations | Required | 7.B | 1 HR |  |  | HR / Admin
| D. | Checking of the Completeness of Onboarding Activities | Required | 7.C | 1 HR |  |  | Operations